## 风险列表
| Risk statement |  | Happening Probability | the level of danger | Response plan | Responsible Person
# | Station | Effect | （0-100%） | （1-10）
1 | Demand changes after entering the design or implementation phase | Directly leads to some of the preliminary work needs to be redone, and then prolongs the entire cycle | 40% | 8 | Communicate fully with users before design, tap the real needs of users, and do detailed needs analysis | Xu Zihan (Team Leader)
2 | Module encoding time exceeded expectations | Slows down the overall progress, resulting in the project can not be completed on time | 50% | 6 | After entering the implementation phase, regular meetings will be held to grasp the development progress. | Yang Chenyu(Development Engineer)
3 | Some players use illegal plugins | Dramatically reduces the player's gaming experience and game fairness | 30% | 6 | Conduct a certain degree of research on illegal plug-ins and strengthen supervision mechanisms in areas prone to illegal plug-ins | Kuang Yi(Development Engineer)
5 | LAN can't make the game run normally | Players cannot join in the game successfully or the game may disconnect during the game course. | 40% | 7 | Search for a better method to manage the network | Can Jianzhen(Development Engineer)
6 | There are flashback or sudden slowing down speed | Reduces the player's gaming experience | 60% | 6 | Coordinate with each part to enhance the quality of game running | Kuang Yi(Development Engineer)
7 | Workload exceeds expectations | Makes the development of software difficult to continue | 30% | 7 | Properly plan and deploy before the formal development, determine the workload of each part, and the supervision is continuously followed in the process. | Xu Zihan (Team Leader)
8 | No hidden vulnerabilities are found during the testing process | Buries hidden dangers for the normal operation of the software, resulting in subsequent rework modification. | 60% | 7 | Design a reasonable and comprehensive test method during the test phase, and conduct more tests properly. | Lan Yuting(Development Engineer)
9 | There is a problem with code management | Causes a loss of progress | 20% | 6 | Save and back up in time during the writing process to prevent accidents from happening | Cao Jianzhen(Development Engineer)
10 | Game features need to be updated, extended and maintained | Causes errors in the course of game | 40% | 7 | For the part needing to be enhanced, make an appropriate design and relevant patches | Yang Chenyu(Development Engineer) Lan Yuting(Development Engineer)